## Product Line
S no. | Name | Dept. | Active Sprint | No of Tasks | Tasks completed | Tasks Pending | Tentative End Date | Released in Production (ASIA) | Status | Delayed by U.S | Remarks | Category | Overall Developing Percentage | Status
WIP US
1 | Finance Epic : Ambassador Payout (EPIC) | Sales | June | 98 | 50 | 48 | 2023-08-30 | - | On time |  | Impact on this US work; due to high priority work on i.e Maps | Productity | 35% | Developing